## Cover
SP ENERGY NETWORKS
Transmission Owner Reinforcement Instruction (TORI)
Quarterly Update Report
View of the 275kV WA Overhead Line between Coylton and New Cumnock substations

## Contents
SPT TORI Quarterly Report Q3 2026
Contents
1. | NOA Project Status Updates
- Project progress and milestone status
- Forecast energisation dates
- Delivery programme updates
2. | Phase One TORI Status Updates
- Project progress and milestone status
- Forecast energisation dates
- Delivery programme updates
3. | Report Scope and Context
This report presents a summary of progress against NOA-related TORI projects and Phase 1 TORI projects only. The scope has been deliberately focused to provide stakeholders with visibility of those projects currently progressing through the relevant investment and delivery stages.
This approach reflects the transitional nature of the wider GB connections and network planning reforms, which are reshaping project categorisation, delivery priorities and reporting requirements across the transmission network. As these reforms continue to be implemented, the content and structure of future TORI Quarterly Reports will be reviewed to ensure continued alignment with industry and regulatory expectations.
Notes:
Due to the ongoing implementation of connections reform and the resulting reassessment of project scope, sequencing and delivery timescales, SP Transmission is not currently in a position to provide reliable updates against the standard delivery stage categories of Design, Consenting, Detailed Engineering, Tendering, Construction and Commissioning Close Out. Reporting against these stages has therefore been suspended for this reporting period to avoid presenting information that may not accurately reflect current project status. The approach will be reviewed as reforms are implemented and project delivery plans become more certain.

## TORI Project Status Updates
TORI Project Status Updates
NOA Project | Project Reference | Project Name | Project Description | Forecast Energisation Date | Energisation Date Under Review? | Design | Consenting | Detailed Engineering | Tendering | Construction | Commissioning Close Out
DLUP | SPT-RI-2085 | DLUP-Windyhill-Lambhill-Denny North 400kV Reinforcement | N/A | 2030-10-30 | N/A
BDUP | SPT-RI-1560 | Beauly Denny 275kV circuit upgrade to 400kV operation | N/A | 12/30/2030 | N/A
DNEU | SPT-RI-246 | Denny North 400/275 kV SGT2 | N/A | 09/30/2026 | N/A
DWNO | SPT-RI-003 | DWNO-Denny to Wishaw 400kV Reinforcement | N/A | 2031-12-05 | N/A
DWUP | SPT-RI-2083 | DWUP-Kincardine - Wishaw 400kV Reinforcement | N/A | 2030-08-30 | N/A
E2DC | SPT-RI-124 SPT-RI-126 SPT-RI-267 | Eastern Subsea HVDC Link from Torness to Hawthorn Pit | N/A | 2029 | N/A
EHRE | SPT-RI-231 | EHRE-Elvanfoot - Harker OHL Conductor Replacement | N/A | 2030-11-01 | N/A
LWUP | SPT-RI-2095 | LWUP - Kincardine North 400kV reinforcement | N/A | 2030-10-11 | N/A
TGDC | SPT-RI-1873 | TGDC-Eastern Subsea HVDC Link from Westfield to South Humber | N/A | 2034 | N/A
TKUP | SPT-RI-2073 | TKUP-East Coast Reinforcement Phase 2 | N/A | 2030-12-30 | N/A
VERE | SPT-RI-1797 | VERE-Strathaven to Elvanfoot OHL Conductor Replacement | N/A | 2030-11-01 | N/A
VSRE | SPT-RI-130 | VSRE XH & XJ Routes 400kV Major Refurb | N/A | 2027-10-26 | N/A
CMN3 | SPT-RI- 1795 SPT-RI-2418 SPT-RI-2378 SPT-RI-1738 SPT-RI-2417 | CMN3 - Gala North – Harker Area 400kV OHL New Build | N/A | 2034-10-31 | N/A
NHNC | SPT-RI-3168 | NHNC - New Deer - Harburn 400kV OHL New Build | N/A | 2037 | N/A
WCN2 | SPT-RI-3309 SPT-RI-2876 SPT-RI-2877 SPT-RI-3315 SPT-RI-3498 SPT-RI-3566 | WCN2 - West Coast Onshore – 400kV OHL New Build | N/A | 2036-12-18 | N/A
HGNC | SPT-RI-3884 | Harburn New 400kV Line South | N/A | 2035-11-05 | N/A
N/A | SPT-RI-294 | Ewe Hill to Hopsrig collector substations 132kV circuit | Wind farms will connect via a new 132kV collector substation, with individual 33kV points of connection provided for each development. A new 132kV overhead line using Poplar conductor will connect the Hopsrig and Ewe Hill collector substations, providing continuous ratings of up to 167MVA pre-fault and 199MVA post-fault in winter conditions. | 2028-02-01 | N/A
N/A | SPT-RI-2415 | AA Route OHL Uprate | The AA route will be thermally uprated from 50°C to 65°C operation using the existing 425mm² AAAC Totara conductor, increasing the pre-fault circuit rating to 180MVA and aligning with the combined firm capacity of the Bathgate and Drumcross GSPs. The uprating will avoid generation curtailment associated with the existing thermal limits of the overhead line. | 2030-08-21 | N/A
N/A | SPT-RI-2510 | Saltcoats A GT OLP | A Load Management Scheme (LMS) will be installed at Saltcoats “A” 132/33kV GSP to prevent transformer overloads during N-1 conditions. The scheme will monitor LV-side transformer current and voltage and provide staged import and export signals to SPD-connected embedded generation at 95%, 100% and 120% of transformer rating to facilitate the disconnection of non-firm connections where required. | 2028-10-27 | N/A
N/A | SPT-RI-2591 | Stirling GSP GT1 (2) LMS Scheme | A Load Management Scheme (LMS) will be installed at Stirling 132/33kV GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2029-04-30 | N/A
N/A | SPT-RI-2731 | Dumfries Grid Transformer Load Management Scheme | A Load Management Scheme (LMS) will be installed at Dumfries 132/33kV GSP to continuously monitor transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2030-05-31 | N/A
N/A | SPT-RI-2741 | Dumfries – Chapelcross 132kV No.2 Circuit (BR Route) Load Management Scheme | A Load Management Scheme (LMS) will be installed at Chapelcross 132kV to continuously monitor loading on the Dumfries–Chapelcross No.2 132kV circuit and prevent overloads following the loss of the adjacent circuit. The scheme will monitor circuit current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of circuit rating to enable the management of connected generation where required. | 2030-05-31 | N/A
N/A | SPT-RI-3010 | Cupar GSP Loss of Mains Signals | A Loss of Mains intertrip scheme will be installed at Cupar GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Cupar GSP, with SPD responsible for the design and installation of the scheme. | 2028-04-25 | N/A
N/A | SPT-RI-3015 | Elderslie GSP 132/33kV Grid T1 & T2 (LMS) | A Load Management Scheme (LMS) will be installed at Elderslie GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded generation where required. | 2028-06-28 | N/A
N/A | SPT-RI-3016 | Elderslie GSP Loss of Mains Signals | A Loss of Mains protection scheme will be installed at Elderslie GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1A and Grid 2A circuit breakers at Elderslie GSP, with SPD responsible for the design and installation of the scheme. | 2028-06-28 | N/A
N/A | SPT-RI-3262 | East Kilbride South GSP SGTs LMS | A Load Management Scheme (LMS) will be installed at East Kilbride South 275/33kV GSP to continuously monitor SGT1 and SGT2 transformer loading and prevent overloads following the loss of a transformer. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded generation operating in export mode where required. | 2026-12-11 | N/A
N/A | SPT-RI3263 | Erskine 132kV Bus Section Circuit Breaker | A new 132kV bus section circuit breaker will be installed at Erskine 132kV substation to create a single-switch arrangement and maintain security of supply following the removal of the BRAP-ERSK No.1 circuit from service. | 2027-08-03 | N/A
N/A | SPT-RI-3285 | Devol Moor-Erskine-Braehead Park 132kV LMS -BZ Route Monitoring Upgrade | The existing Devol Moor–Erskine–Braehead Park Load Management Scheme (LMS) will be extended to manage thermal loading on the Erskine–Braehead Park 132kV circuit. A new monitoring outstation will be installed at Braehead Park, with staged signals issued at 95%, 100% and 120% of circuit rating to enable the management of non-firm embedded generation and transmission-connected sites where required. | 2030-10-31 | N/A
N/A | SPT-RI-3530 | Johnstone GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Johnstone GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Johnstone GSP, with SPD responsible for the design and installation of the scheme. | 2028-07-28 | N/A
N/A | SPT-RI-3625 | Kaimes B GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Kaimes B GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Supergrid 1 Switch B and Supergrid 2 Switch B circuit breakers at Kaimes B GSP, with SPD responsible for the design and installation of the scheme. | 2029-10-01 | N/A
N/A | SPT-RI-3639 | CLYM Westburn Rd GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Clyde’s Mill (Westburn Road) GSP to mitigate the risk of islanding on the SPD network. The scheme will monitor the status of the Supergrid 1 and Supergrid 2 circuit breakers and issue trip signals to disconnect embedded generation where required. | 2027-05-31 | N/A
N/A | SPT-RI-3857 | Crookston B GSP Loss of Mains Signals | A Loss of Mains protection scheme will be installed at Crookston B GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Crookston B GSP, with SPD responsible for the design and installation of the scheme. | 2029-09-28 | N/A
N/A | SPT-RI-3858 | Crookston B GSP LVDOC Protection Modifications | The existing low-voltage directional overcurrent protection at Crookston B GSP will be replaced with new equipment to ensure protection schemes operate correctly during periods of high export from the 33kV network. | 2029-09-28 | N/A
N/A | SPT-RI-4035 | Giffnock GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Giffnock GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Supergrid 1 and Supergrid 2 circuit breakers at Giffnock GSP, with SPD responsible for the design and installation of the scheme. | 2029-10-31 | N/A
N/A | SPT-RI-4113 | Drumcross GSP LOM Signals | A Loss of Mains intertrip scheme will be installed at Drumcross GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the GT1 and GT2 circuit breakers at Drumcross GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31 | N/A
N/A | SPT-RI-4117 | Eccles GSP Loss of Mains Signals | A Loss of Mains intertrip scheme will be installed at Eccles GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 33kV circuit breakers at Eccles GSP, with SPD responsible for the design and installation of the scheme. | 2029-09-29 | N/A
N/A | SPT-RI-4145 | Devol Moor 132/33kV GSP LMS | A Load Management Scheme (LMS) will be installed at Devol Moor GSP to continuously monitor GT1A and GT2A transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of the Ardgowan Estate embedded connection where required. | 2030-10-31 | N/A
N/A | SPT-RI-4191 | Easterhouse GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Easterhouse GSP to mitigate the risk of islanding on the SPD network. The scheme will monitor the status of the Supergrid 1 Switch A and Supergrid 2 Switch A circuit breakers and issue trip signals to disconnect embedded generation where required, with SPD responsible for the design and installation of the scheme. | 2029-04-30 | N/A
N/A | SPT-RI-4261 | Crookston GSP Voltage Control Scheme Upgrade | The existing AVC relay at Crookston GSP will be replaced with a modern equivalent capable of operating under reverse power flow conditions, ensuring effective voltage control during periods of network export. | 28/09.2029 | N/A
N/A | SPT-RI-4595 | Cupar GSP GT2 LVDOC Removal | The existing LVDOC relay on T2 at Cupar 132/33kV GSP will be replaced with a second intertrip scheme to enable full reverse power flow through the transformer up to its rated capacity, in line with SPEN policy requirements. This follows the equivalent modification previously completed on T1. | 2028-04-25 | N/A
N/A | SPT-RI-4631 | Dumfries GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Dumfries GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1B, Grid 2B and Grid 4 circuit breakers at Dumfries GSP, with SPD responsible for the design and installation of the scheme. | 2030-05-31 | N/A
N/A | SPT-RI-4645 | Bonnybridge GSP Load Management Scheme | A Load Management Scheme (LMS) will be installed at Bonnybridge GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2029-06-21 | N/A
N/A | SPT-RI-4646 | Bonnybridge GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Bonnybridge GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Bonnybridge GSP, with SPD responsible for the design and installation of the scheme. | 2029-06-21 | N/A
N/A | SPT-RI-4647 | Stirling GSP Loss of Mains Scheme | A Loss of Mains protection scheme will be installed at Stirling GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Stirling GSP, with SPD responsible for the design and installation of the scheme. | 2029-04-30 | N/A
N/A | SPT-RI-4648 | Bathgate GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Bathgate GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Bathgate GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31 | N/A
N/A | SPT-RI-4649 | Cumbernauld GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Cumbernauld GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Cumbernauld GSP, with SPD responsible for the design and installation of the scheme. | 2028-10-27 | N/A
N/A | SPT-RI-4650 | Saltcoats A 132/33kV GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Saltcoats A 132/33kV GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 (GTA1) and Grid 2 (GTA2) circuit breakers at Saltcoats A GSP, with SPD responsible for the design and installation of the scheme. | 2028-10-27 | N/A
N/A | SPT-RI-4660 | Devol Moor GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Devol Moor GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1A and Grid 2A circuit breakers at Devol Moor GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31 | N/A
N/A | SPT-RI-4670 | Stirling GSP LVDOC Removal | The existing LVDOC relays on GT1 and GT2 at Stirling 132/33kV GSP will be replaced with second intertrip schemes to enable full reverse power flow through the transformers up to their rated capacity, in line with SPEN policy requirements. | 2029-04-30 | N/A
N/A | SPT-RI-4673 | Fallago 400kV Substation Extension | Fallago 400kV Substation will be extended with a new 400kV double busbar bay and a new 400/132kV, 240MVA transformer to provide points of connection for new developments. The works will include the installation of associated 400kV circuit breaker and line disconnector equipment. | 2029-04-30 | N/A