## Cover
SPT TORI Quarterly Report

## Content
SPT TORI Quarterly Report
It should be noted that the contracted programme dates included in this report are subject to change pursuant to the terms of the relevant contracts. The information contained in this report, including project dates and delivery timelines, is provided for general information purposes only and on a non-reliance basis - it does not constitute a representation, warranty, or guarantee as to the actual or anticipated delivery dates of any project.
Contents
1. NOA Project Status Updates
- Forecast energisation dates
As part of ongoing improvements to project reporting, the NOA Projects section of the TORI Quarterly Report will now present delivery against the contracted programme dates used across Developer reporting. This provides a more consistent basis for reporting and supports a clearer view of project progress across the portfolio.
2. Phase One TORI Status Updates
- Forecast energisation dates
3. Report Scope and Context
This report presents a summary of progress against NOA-related TORI projects and Phase 1 TORI projects only. The scope has been deliberately focused to provide stakeholders with visibility of those projects currently progressing through the relevant investment and delivery stages.
This approach reflects the transitional nature of the wider GB connections and network planning reforms, which are reshaping project categorisation, delivery priorities and reporting requirements across the transmission network. As these reforms continue to be implemented, the content and structure of future TORI Quarterly Reports will be reviewed to ensure continued alignment with industry and regulatory expectations.

## TORI Project Status Updates
NOA Project | Project Reference | Project Name | Project Description | Contracted Energisation Date | Design | Consenting | Detailed Engineering | Tendering | Construction | Commissioning Close Out
DLUP | SPT-RI-2085 | DLUP-Windyhill-Lambhill-Denny North 400kV Reinforcement | The reinforcement establishes a new 400kV transmission route by upgrading existing infrastructure to support increased power transfers and wider network reinforcement requirements. The scheme includes a new 400kV circuit connection between major substations, improving network capacity, resilience, and integration with offshore and onshore transmission developments. | 2029-10-01
BDUP | SPT-RI-1560 | Beauly Denny 275kV circuit upgrade to 400kV operation | The reinforcement upgrades an existing transmission circuit from 275kV to 400kV operation through modifications at an existing substation. The scheme will increase network capacity and support higher power transfers across the transmission system. | 2029-10-31
DNEU | SPT-RI-246 | Denny North 400/275 kV SGT2 | The reinforcement includes installation of additional 400/275kV transformation capacity and associated substation equipment to increase network transfer capability. The scheme will strengthen the transmission system and support the connection and export of generation by increasing thermal capacity across key network boundaries. | 2025-03-31
DWNO | SPT-RI-003 | DWNO-Denny to Wishaw 400kV Reinforcement | The reinforcement delivers a new 400kV transmission corridor, associated substation infrastructure, and uprating of existing overhead line routes to increase north-south transfer capability and support future generation and demand growth. The scheme establishes new 400kV and 275kV circuit connections, creates additional transformation capacity, and modernises existing assets to maximise network capacity, resilience, and operational flexibility. | 2030-10-31
DWUP | SPT-RI-2083 | DWUP-Kincardine - Wishaw 400kV Reinforcement | The reinforcement establishes a new 400kV substation and associated transformation capacity to increase network transfer capability and support growing renewable generation flows through the transmission system. The scheme includes new 400/275kV transformation assets, associated substation infrastructure, and network reconfiguration works, while providing for future expansion and additional 400kV connectivity. | 2027-12-31
E2DC | SPT-RI-124 | Eastern Subsea HVDC Link from Torness to Hawthorn Pit | The reinforcement comprises a new 400kV substation, a high-capacity HVDC link, and associated reactive compensation equipment to increase network transfer capability and support large-scale power flows between Scotland and England. The scheme provides new transmission connection points, strengthens network resilience and voltage performance, and facilitates the integration and export of renewable generation. | 2028-10-31
| SPT-RI-126 |  |  | 2029-04-24
| SPT-RI-267 |  |  | 2026-07-24
EHRE | SPT-RI-231 | EHRE-Elvanfoot - Harker OHL Conductor Replacement | The reinforcement upgrades an existing 400kV overhead line through conductor and earthwire replacement to increase thermal capacity and enable higher power transfers. The scheme strengthens a strategic transmission route, supporting increased transfer capability between Scotland and England while improving asset performance and network resilience. | 2030-11-01
LWUP | SPT-RI-2095 | LWUP - Kincardine North 400kV reinforcement | The reinforcement establishes a new 400kV GIS substation to increase transmission capacity, support growing renewable generation transfers, and facilitate the replacement of ageing network infrastructure. The scheme includes connections to multiple existing 400kV circuits, high-capacity transformation assets, and provision for future network expansion, including additional circuit connections, shunt reactors, and reactive compensation equipment. | 2027-12-31
TGDC | SPT-RI-1873 | TGDC-Eastern Subsea HVDC Link from Westfield to South Humber | The reinforcement delivers a new 2GW HVDC transmission link and associated onshore network infrastructure to increase transfer capability between Scotland and England. The scheme includes subsea and onshore transmission assets, together with supporting AC network reinforcements at both terminals, enhancing network capacity, resilience, and the integration of renewable generation. | 2031-10-31
TKUP | SPT-RI-2073 | TKUP-East Coast Reinforcement Phase 2 | The reinforcement upgrades existing transmission infrastructure from 275kV to 400kV operation to increase network transfer capability and support growing power flows on the east coast. The scheme maximises the capacity of existing overhead line assets, strengthening network resilience and facilitating the integration of major transmission and renewable energy developments. | 2030-10-31
VERE | SPT-RI-1797 | VERE-Strathaven to Elvanfoot OHL Conductor Replacement | The reinforcement upgrades existing 400kV overhead line circuits with high-capacity conductors to increase thermal ratings and accommodate growing generation output. The scheme strengthens a key transmission corridor, enabling higher power transfers while improving network capacity and operational resilience. | 2030-10-31
VSRE | SPT-RI-130 | VSRE XH & XJ Routes 400kV Major Refurb | The reinforcement upgrades existing 400kV overhead line routes with higher-capacity conductor systems to increase thermal ratings and support increased power transfers across the transmission network. The scheme enhances network capacity and operational resilience while maintaining the existing circuit configuration. | 2028-02-15
CMN3 | SPT-RI-1795 | CMN3 - Gala North – Harker Area 400kV OHL New Build | The reinforcement package delivers new 400kV transmission infrastructure, transformation capacity, and overhead line connections to increase transfer capability across the Scotland-England boundary and support continued growth in renewable generation. The scheme includes new 400/132kV substations, additional transformer capacity, approximately 100km of new 400kV double-circuit overhead lines, associated substation extensions, and load management arrangements to maintain secure network operation under outage conditions. | 2033-05-30
| SPT-RI-2378 |  |  | 2034-07-03
| SPT-RI-1738 |  |  | 2033-05-30
| SPT-RI-2417 |  |  | 2033-05-30
NHNC | SPT-RI-3168 | NHNC - New Deer - Harburn 400kV OHL New Build | The reinforcement establishes a new 132kV substation and associated transformation capacity to support new generation connections and integrate with future 400kV network developments. The scheme includes new 400/132kV transformers, 132kV switchgear infrastructure, and provision for future network expansion, increasing connection capacity, operational flexibility, and network resilience. | 2031-06-30
WCN2 | SPT-RI-3309 | WCN2 - West Coast Onshore – 400kV OHL New Build | The reinforcement package establishes a new west coast 400kV transmission corridor to support significant growth in renewable generation and increase transfer capability across the wider transmission network. The scheme includes new 400kV and 275kV substations, additional transformation capacity, new 400kV double-circuit overhead lines, strategic network uprating works, and associated substation infrastructure, creating a high-capacity transmission route and enhancing network resilience, flexibility, and cross-border power transfer capability. | 2033-10-31
| SPT-RI-2876 |  |  | 2037-10-31
| SPT-RI-2877 |  |  | 2036-10-31
| SPT-RI-3315 |  |  | 2033-10-31
| SPT-RI-3498 |  |  | 2036-10-31
| SPT-RI-3566 |  |  | 2037-10-30
HGNC | SPT-RI-3884 | Harburn New 400kV Line South | The reinforcement establishes a new 400kV transmission connection and associated substation infrastructure to increase network transfer capability and support future generation growth. The scheme includes approximately 60km of new 400kV double-circuit overhead line, associated 400kV switchgear connections, and enhancements at both terminal substations to improve network capacity, resilience, and operational flexibility. | 2036-10-31
N/A | SPT-RI-173 | Glenglass to Glenmuckloch 132kV OHL | Generation in the area will connect via a new 132kV double-circuit extension and collector substation. The scheme includes expansion of an existing GIS substation, approximately 10km of new steel lattice tower overhead line, and a new 132kV double busbar collector substation to provide the required network capacity and connectivity. | 2029-10-31
N/A | SPT-RI-221 | Kendoon to Glenlee 132kV reinforcements | The reinforcement extends the high-capacity 132kV double-circuit network to increase transfer capability between the local generation group and the wider transmission system. The scheme includes new high-capacity overhead line infrastructure and substation modifications to accommodate the connection, improve network connectivity, and remove existing transfer constraints. | 2030-03-08
N/A | SPT-RI-222 | Glenlee to Tongland 132kV Modernisation | The modernisation includes construction of a new 132kV double-circuit overhead line to increase transfer capability to the wider transmission system and strengthen local network boundaries. The scheme will remove existing circuit constraints, improving network capacity, resilience, and operational flexibility. | 2031-11-20
N/A | SPT-RI-236 | Glenmuckloch to ZV Route Reinforcements | The reinforcement introduces a new 400kV connection to support increasing generation volumes and relieve constraints across the transmission network. The scheme includes new 400/132kV transformation capacity, a new 400kV overhead line connection, associated substation infrastructure, and load management arrangements to maintain secure operation under outage conditions. The design allows for future expansion to a full 400kV substation configuration as additional network reinforcements are delivered. | 2030-10-31
N/A | SPT-RI-294 | Ewe Hill to Hopsrig collector substations 132kV circuit | Wind farms will connect via a new 132kV collector substation, with individual 33kV points of connection provided for each development. A new 132kV overhead line using Poplar conductor will connect the Hopsrig and Ewe Hill collector substations, providing continuous ratings of up to 167MVA pre-fault and 199MVA post-fault in winter conditions. | 2028-02-01
N/A | SPT-RI-2415 | AA Route OHL Uprate | The AA route will be thermally uprated from 50°C to 65°C operation using the existing 425mm² AAAC Totara conductor, increasing the pre-fault circuit rating to 180MVA and aligning with the combined firm capacity of the Bathgate and Drumcross GSPs. The uprating will avoid generation curtailment associated with the existing thermal limits of the overhead line. | 2030-08-21
N/A | SPT-RI-2510 | Saltcoats A GT OLP | A Load Management Scheme (LMS) will be installed at Saltcoats “A” 132/33kV GSP to prevent transformer overloads during N-1 conditions. The scheme will monitor LV-side transformer current and voltage and provide staged import and export signals to SPD-connected embedded generation at 95%, 100% and 120% of transformer rating to facilitate the disconnection of non-firm connections where required. | 2028-10-27
N/A | SPT-RI-2591 | Stirling GSP GT1 (2) LMS Scheme | A Load Management Scheme (LMS) will be installed at Stirling 132/33kV GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2029-04-30
N/A | SPT-RI-2731 | Dumfries Grid Transformer Load Management Scheme | A Load Management Scheme (LMS) will be installed at Dumfries 132/33kV GSP to continuously monitor transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2030-05-31
N/A | SPT-RI-2741 | Dumfries – Chapelcross 132kV No.2 Circuit (BR Route) Load Management Scheme | A Load Management Scheme (LMS) will be installed at Chapelcross 132kV to continuously monitor loading on the Dumfries–Chapelcross No.2 132kV circuit and prevent overloads following the loss of the adjacent circuit. The scheme will monitor circuit current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of circuit rating to enable the management of connected generation where required. | 2031-08-31
N/A | SPT-RI-3010 | Cupar GSP Loss of Mains Signals | A Loss of Mains intertrip scheme will be installed at Cupar GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Cupar GSP, with SPD responsible for the design and installation of the scheme. | 2028-04-25
N/A | SPT-RI-3015 | Elderslie GSP 132/33kV Grid T1 & T2 (LMS) | A Load Management Scheme (LMS) will be installed at Elderslie GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded generation where required. | 2028-06-28
N/A | SPT-RI-3016 | Elderslie GSP Loss of Mains Signals | A Loss of Mains protection scheme will be installed at Elderslie GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1A and Grid 2A circuit breakers at Elderslie GSP, with SPD responsible for the design and installation of the scheme. | 2028-06-28
N/A | SPT-RI-3262 | East Kilbride South GSP SGTs LMS | A Load Management Scheme (LMS) will be installed at East Kilbride South 275/33kV GSP to continuously monitor SGT1 and SGT2 transformer loading and prevent overloads following the loss of a transformer. The scheme will monitor LV-side transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded generation operating in export mode where required. | 2026-12-11
N/A | SPT-RI-3263 | Erskine 132kV Bus Section Circuit Breaker | A new 132kV bus section circuit breaker will be installed at Erskine 132kV substation to create a single-switch arrangement and maintain security of supply following the removal of the BRAP-ERSK No.1 circuit from service. | 2027-08-03
N/A | SPT-RI-3285 | Devol Moor-Erskine-Braehead Park 132kV LMS -BZ Route Monitoring Upgrade | The existing Devol Moor–Erskine–Braehead Park Load Management Scheme (LMS) will be extended to manage thermal loading on the Erskine–Braehead Park 132kV circuit. A new monitoring outstation will be installed at Braehead Park, with staged signals issued at 95%, 100% and 120% of circuit rating to enable the management of non-firm embedded generation and transmission-connected sites where required. | 2030-10-31
N/A | SPT-RI-3530 | Johnstone GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Johnstone GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Johnstone GSP, with SPD responsible for the design and installation of the scheme. | 2028-06-28
N/A | SPT-RI-3625 | Kaimes B GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Kaimes B GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Supergrid 1 Switch B and Supergrid 2 Switch B circuit breakers at Kaimes B GSP, with SPD responsible for the design and installation of the scheme. | 2029-10-01
N/A | SPT-RI-3639 | CLYM Westburn Rd GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Clyde’s Mill (Westburn Road) GSP to mitigate the risk of islanding on the SPD network. The scheme will monitor the status of the Supergrid 1 and Supergrid 2 circuit breakers and issue trip signals to disconnect embedded generation where required. | 2027-05-31
N/A | SPT-RI-3857 | Crookston B GSP Loss of Mains Signals | A Loss of Mains protection scheme will be installed at Crookston B GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Crookston B GSP, with SPD responsible for the design and installation of the scheme. | 2029-09-28
N/A | SPT-RI-3858 | Crookston B GSP LVDOC Protection Modifications | The existing low-voltage directional overcurrent protection at Crookston B GSP will be replaced with new equipment to ensure protection schemes operate correctly during periods of high export from the 33kV network. | 2029-09-28
N/A | SPT-RI-4035 | Giffnock GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Giffnock GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Supergrid 1 and Supergrid 2 circuit breakers at Giffnock GSP, with SPD responsible for the design and installation of the scheme. | 2029-10-31
N/A | SPT-RI-4113 | Drumcross GSP LOM Signals | A Loss of Mains intertrip scheme will be installed at Drumcross GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the GT1 and GT2 circuit breakers at Drumcross GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31
N/A | SPT-RI-4117 | Eccles GSP Loss of Mains Signals | A Loss of Mains intertrip scheme will be installed at Eccles GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 33kV circuit breakers at Eccles GSP, with SPD responsible for the design and installation of the scheme. | 2029-09-29
N/A | SPT-RI-4145 | Devol Moor 132/33kV GSP LMS | A Load Management Scheme (LMS) will be installed at Devol Moor GSP to continuously monitor GT1A and GT2A transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of the Ardgowan Estate embedded connection where required. | 2030-10-31
N/A | SPT-RI-4191 | Easterhouse GSP Loss of Mains | A Loss of Mains intertrip scheme will be installed at Easterhouse GSP to mitigate the risk of islanding on the SPD network. The scheme will monitor the status of the Supergrid 1 Switch A and Supergrid 2 Switch A circuit breakers and issue trip signals to disconnect embedded generation where required, with SPD responsible for the design and installation of the scheme. | 2029-04-30
N/A | SPT-RI-4261 | Crookston GSP Voltage Control Scheme Upgrade | The existing AVC relay at Crookston GSP will be replaced with a modern equivalent capable of operating under reverse power flow conditions, ensuring effective voltage control during periods of network export. | 2029-09-28
N/A | SPT-RI-4595 | Cupar GSP GT2 LVDOC Removal | The existing LVDOC relay on T2 at Cupar 132/33kV GSP will be replaced with a second intertrip scheme to enable full reverse power flow through the transformer up to its rated capacity, in line with SPEN policy requirements. This follows the equivalent modification previously completed on T1. | 2028-04-25
N/A | SPT-RI-4631 | Dumfries GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Dumfries GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1B, Grid 2B and Grid 4 circuit breakers at Dumfries GSP, with SPD responsible for the design and installation of the scheme. | 2031-08-31
N/A | SPT-RI-4645 | Bonnybridge GSP Load Management Scheme | A Load Management Scheme (LMS) will be installed at Bonnybridge GSP to continuously monitor GT1 and GT2 transformer loading and prevent unacceptable overloading of primary transmission equipment. The scheme will monitor transformer current and voltage and provide staged signals to SP Distribution at 95%, 100% and 120% of transformer rating to enable the management of embedded connections where required. | 2029-06-21
N/A | SPT-RI-4646 | Bonnybridge GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Bonnybridge GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Bonnybridge GSP, with SPD responsible for the design and installation of the scheme. | 2029-06-21
N/A | SPT-RI-4647 | Stirling GSP Loss of Mains Scheme | A Loss of Mains protection scheme will be installed at Stirling GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Stirling GSP, with SPD responsible for the design and installation of the scheme. | 2029-01-31
N/A | SPT-RI-4648 | Bathgate GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Bathgate GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Bathgate GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31
N/A | SPT-RI-4649 | Cumbernauld GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Cumbernauld GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 and Grid 2 circuit breakers at Cumbernauld GSP, with SPD responsible for the design and installation of the scheme. | 2028-10-27
N/A | SPT-RI-4650 | Saltcoats A 132/33kV GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Saltcoats A 132/33kV GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1 (GTA1) and Grid 2 (GTA2) circuit breakers at Saltcoats A GSP, with SPD responsible for the design and installation of the scheme. | 2028-10-27
N/A | SPT-RI-4660 | Devol Moor GSP Loss of Mains | A Loss of Mains protection scheme will be installed at Devol Moor GSP to mitigate the risk of islanding on the SPD network. SPT will provide the status of the Grid 1A and Grid 2A circuit breakers at Devol Moor GSP, with SPD responsible for the design and installation of the scheme. | 2030-10-31
N/A | SPT-RI-4670 | Stirling GSP LVDOC Removal | The existing LVDOC relays on GT1 and GT2 at Stirling 132/33kV GSP will be replaced with second intertrip schemes to enable full reverse power flow through the transformers up to their rated capacity, in line with SPEN policy requirements. | 2029-01-31
N/A | SPT-RI-4673 | Fallago 400kV Substation Extension | Fallago 400kV Substation will be extended with a new 400kV double busbar bay and a new 400/132kV, 240MVA transformer to provide points of connection for new developments. The works will include the installation of associated 400kV circuit breaker and line disconnector equipment. | 2029-04-30